Sexual and Reproductive Health in Humanitarian Crises

Consultancy on Disability Inclusion

IPPF’s Humanitarian Programme seeks to improve access to life-saving sexual and reproductive health for affected communities, with a focus on hard-to-reach and marginalized groups, including women, youth and persons with disabilities. Member Associations (MAs) implementing preparedness programs and / or responding in natural disaster and conflict settings have varying awareness and experience relating to disability inclusion, with some MAs already expanding their networks to the disability community. A capacity development strategy is needed to support more systemic and sustained capacity development on disability inclusion across the IPPF Humanitarian Programme.

The wider goal is to develop a structure and process for participatory monitoring, evaluation and learning on disability inclusion in humanitarian crises with Member Associations. The first phase of the consultancy will focus on:

- Identifying entry points for strengthening inclusion in IPPF systems and processes; and,

- Drafting a foundational resource on disability inclusion which will be used to raise awareness and engage MAs in future capacity building activities.

| Activity | Time frame | Days of work |
| --- | --- | --- |
| Review reports, tools and other resources to map entry points for disability inclusion in the system and processes of IPPFs humanitarian programme. | By 2nd Nov | 3 days (remote) |
| Interviews with key IPPF staff to identify capacity development tools and resources for future disability inclusion. | By 2nd Nov | 1 day (remote) |
| Capacity development plan – Document entry points and possible “products” that could form foundational resources guiding future capacity development initiatives on disability inclusion. Present/Review need for dedicated technical support, development of complementary tools and resources, like a self-assessment tool. What are the other systems for capacity-building where we can adapt a tools, scale up , complementary, multi-proned approach | By 2nd Nov | 1 day (remote) |
| Feedback from IPPF on capacity development plan and prioritize foundational resources. | By 9th Nov | N/A – Skype meeting |
| Draft one foundational resource (e.g. guidance document, mapping tool or orientation package) which can be later integrated into IPPF systems and processes. | By 16th Nov | 4 days (remote) |
| IPPF staff review the foundational resource. Reflective learning, formative. | By 30th Nov | N/A – Skype meeting |
| Finalize foundational resource based on feedback from IPPF staff. | By 7th Dec | 1 day |
| Total |  | 10 days |

Deliverables

- Capacity development plan (approx. 2 pages) detailing entry points identified, possible “products” and recommendations for longer term capacity development. Submitted 2nd November 2018.

- One foundational resource (e.g. guidance document, mapping tool or orientation package) – to be decided based on the capacity development plan and in consultation with IPPF staff. Submitted 7th December 2018.