# Terms of Reference (TOR)

Consultancy for the Design and Facilitation of the IPPF Directors’ Leadership Team (DLT)

Reinvention and Strategic Alignment Retreat

International Planned Parenthood Federation (IPPF)

Director-General’s Office

Duration: 8–10 weeks (including design, facilitation, and post-retreat outputs)

Location: Hybrid (virtual preparation + in-person retreat)

Retreat Date: 20 to 24 of March, near London.

## 1. Background

The International Planned Parenthood Federation (IPPF) is entering a new phase of strategic renewal under the leadership of the incoming Director-General (DG), beginning her tenure in March 2026. To ensure a cohesive, high-performing, and future-ready Secretariat and a strong Federation, we IPPF are seeking to ensure  the Directors’ Leadership Team (DLT) works as a unified, strategically aligned, and values-driven executive body.

The DLT is central to:

- Translating the 2023–2028 Strategic Framework into coherent operational leadership

- Ensuring organizational stability and internal cohesion

- Strengthening collaboration within  Secretariat offices/divisions and  with Member Associations

- Modeling feminist, inclusive, and decolonial leadership practices

- Embedding accountability, transparency, and shared stewardship at the highest levels

- Given the political and operational complexity of the global SRHR landscape, including funding shifts, anti-rights and anti-gender backlash, internal cultural needs, evolving expectations from donors, and federation governance dynamics, it is fundamental that DLT operates with strategic clarity, psychological safety, trust, and collective purpose.

IPPF therefore seeks a specialized consultancy to design and facilitate an inaugural DLT Reinvention Retreat and produce follow-up documentation to establish a sustainable and effective leadership culture.

## 2. Purpose of the Consultancy

To design, facilitate, and document a transformational leadership retreat for IPPF’s Directors’ Leadership Team that:

- Reinstalls and redefines the DLT’s purpose, mandate, working norms, and culture.

- Establishes trust, cohesion, and shared accountability among the members of the DLT.

- Clarifies roles, decision-making frameworks, communication channels, and escalation protocols within the DLT.

- Embeds feminist, distributive, inclusive, and psychologically safe leadership approaches.

- Produces tangible leadership tools that guide the DLT’s work beyond the retreat.

The consultancy should propose effective methodology, blending:

- Systems thinking

- Feminist leadership

- Organizational development

- Political acumen

- Facilitation of complex, diverse global teams

- Strategic planning and alignment tools

- Experiential learning

## 3. Scope of Work & Deliverables

### Phase 1 – Discovery & Diagnostic (Weeks 1–3)

The consultant will:

- Conduct confidential interviews with the DG, all Directors, and selected stakeholders.

- Review existing organizational documents (strategy, performance, culture surveys).

- Assess current DLT dynamics, trust levels, communication patterns, strengths, and gaps.

- Identify core challenges and opportunities for leadership transformation.

- Draft a Diagnostic Summary Report outlining insights and priorities.

Deliverable 1: Diagnostic Summary Report

Including:

- Current strengths, risks, and cultural dynamics

- Leadership alignment gaps

- Recommendations for retreat design

- Initial hypotheses for DLT operating model

### Phase 2 – Retreat Design (Weeks 4–6)

The consultant will develop:

- Full agenda (3 days in-person)

- Thematic modules (trust-building, strategic alignment, decision-making, accountability, etc.)

- Experiential and reflective activities

- Pre-reading and exercises for DLT members

Design must integrate:

- Feminist and inclusive leadership methodology

- Anti-oppressive, norm critical and decolonial approaches

- Psychological safety practices

- Strategic clarity and execution frameworks

- Power, conflict, and influence mapping

- Organizational values and culture shaping

Deliverable 2: Full Retreat Design Pack

Including: agenda, materials, exercises, facilitator scripts, and success metrics.

### Phase 3 – Retreat Facilitation (3 days)

The consultant team will:

- Facilitate the retreat with high-level political and interpersonal sensitivity

- Guide Directors through dialogue, reflection, and co-creation

- Manage tensions, conflict, and relationship-building

- Generate real-time documentation

Retreat topics may include:

- Leadership identity & collective purpose

- Trust and vulnerability in executive teams

- How power operates in federated systems

- Decision-making & accountability

- Role clarity and boundaries

- Cross-regional/Secretariat collaboration

- Conflict navigation

- Collective stewardship of organizational culture

- The DLT Operating Model 2026

Deliverable 3: Retreat Facilitation

A highly professional, safe, generative experience.

### Phase 4 – Post-Retreat Outputs (Weeks 8–10)

The consultants will produce a DLT Leadership Foundation Package, including:

- Revised DLT Mandate & Terms of Reference

- DLT Operating Model (decision-rights, meeting rhythms, communication pathways)

- Leadership Charter (values, behaviors, commitments)

- Conflict Resolution Protocol

- Accountability Framework

- 90-Day DLT Strengthening Plan

- Recommendations for ongoing coaching or team development

Deliverable 4: Leadership Foundation Package

## 4. Required Expertise

Consultants must demonstrate:

- Proven experience with executive team reinvention, organizational culture change, and leadership development

- Expertise in feminist, decolonial, norm critical, anti-oppressive organizational design

- Experience working with humanitarian, SRHR, human rights, or global health NGOs

- Ability to navigate complex, multi-regional, politically sensitive environments

- High-level facilitation skills, including managing conflict and power dynamics

- Understanding of governance models and influence patterns in federated organizations

- Experience creating practical leadership frameworks and operating models

- Strong documentation and synthesis capability

- Firms with diverse, intersectional, Global South-led teams are encouraged to apply.

## 5. Level of Effort & Timeline

Estimated:

8–10 weeks total

~20–25 consultant days

Retreat itself: 3 full days in-person (Richmond, London)

Full completion: before end of April 2026

## 6. Reporting & Coordination

The consultancy will report to:

Director-General (designate)

With coordination support from the retreat planning committee comprised by the three directors

## 7. Budget

Applicants must submit:

- Cost proposal (daily rate + travel if applicable)

- Team composition and roles

- Proposed methodology

## 8. Application Requirements

Interested firms/consultants must submit:

- Letter of interest

- Proposed methodology

- CVs of key team members

- Portfolio of similar assignments

- Two references from recent leadership/OD contracts